## 2026 Bid Tracker
Job ID | Month | Client | Project Name | Bid Due Date | Drawing Stage | Bid Type | Sent Date | Sub. Method | Status | Win? | Job Type | Est. Bid Value | Link: Drawings | Link: Specs | Link: Schedule | Notes | Bid Feedback | NTP Received? | Final Cost | Profit Margin ($) | CO Link | Lessons Learned
January
Q-26-003 |  | Viking | Legacy Good Sam Pharmacy Retrofit | 2026-01-16 | CD | Hard Bid | 01/16/2026 | Email | Won | ✔ |  | 47988
Q-26-004 |  | Brian Kasler | Ktichen & Bath Cabinets | 2026-01-19 | Email | Budget | 01/19/2026 | Email | Sent |  | Residential | 58551
Q-26-005 |  | Schommer & Sons | Tualatin Park Office Reno | 2026-01-22 | Bid Set | Hard Bid | 01/22/2026 | BuildingConnected | Sent |  | Renovation | 9481
Q-26-006 |  | Ross Builder | Tualatin Park Office Reno | 2026-01-22 | Bid Set | Hard Bid | 01/22/2026 | BuildingConnected | Sent |  | Renovation | 9481
Q-26-007 |  | Legacy Salmon Creek | 527 Closet Cab | 2026-01-16 | Email | Hard Bid | 01/16/2026 | Email | Sent |  | Healthcare | 1052
Q-26-008 |  | Norwest | Gresham Advanced Dentistry | 2026-01-12 | Email | Budget | 01/14/2026 | Email | Sent |  | Dental | 6150
Q-26-009 |  | Tim- TRBLDG Servies | NW Primary Care- SE Mallard Way | 2026-01-14 | Email | Hard Bid | 01/14/2026 | Email | Won | ✔ |  | 1900
Q-26-010 |  | Manion Design | Back Bar Cabs | 2026-01-15 | Email | Hard Bid |  | Email | Won | ✔ |  | 2325
Q-26-011 |  | OHSU HMC | 8th Ave Ste 205 | 2026-01-16 | Email | Hard Bid | 01/16/2026 | Email | Sent |  | Healthcare | 1147
Q-26-012 |  | OHSU HMC | Rm 1321 Countertop | 2026-01-15 | Email | Hard Bid |  | Email | Won | ✔ | Healthcare | 1180
Q-26-013 |  | Idea Interiors | Coats & Tails Lobby Remodel | 2026-01-14 | Email | Hard Bid |  | Email | Won | ✔ | Commercial TI | 3920
Q-26-014 |  | Five Star | Meridian Park FSB- Corian CT | 2026-01-14 | Email | Hard Bid | 01/14/2026 | Email | Sent |  |  | 7218
Q-26-015 |  | Five Star | Systems Cabinets | 2026-01-15 | Email |  |  | Email | Sent |  |  | 35919
Q-26-016 |  | Five Star | Emanuel Rm 1611 | 2026-01-15 | Email | Hard Bid | 01/14/2026 | Email | Won | ✔ | Healthcare | 5713
Q-26-017 | On Hold | Wilammette Falls | Behavioral Sloped Corian | [5 empty] | On Hold
Q-26-018 |  | Wilammette Falls | ICU Corian CT | 2026-01-15 | Email | Hard Bid | 01/15/2026 | Email | Sent |  | Hospital | 3715
Q-26-019 |  | Wilammette Falls | 17 Cab Drawers w/ servo drive | 2026-01-15 | Email | Hard Bid |  | Email | Sent |  | Hospital | 9930
Q-26-020 |  | VAM | Aligned Hillsboro Campus | 2026-01-15 | Email | Hard Bid |  | Email | Won | ✔ | Commercial | 3622
Q-26-021 |  | Norwest | Stones Dental- Added Scope/ Sterile Revision
Q-26-022 |  | Trainor | Herman Miller Wood Ceiling Install | 2026-01-21 | Email | Hard Bid | 01/21/2026 | Email | Sent |  | Commercial | 25800
Q-26-023 |  | Trainor | Design Within Reach | 2026-01-21 | Email | Hard Bid | 01/21/2026 | Email | Sent |  | Commercial
Q-26-024 |  | Robert Hakes | Elite Recovery | 2026-01-22 | Email | Hard Bid | [5 empty] | 3350
Q-26-025 |  | Essex | Bonneville St Johns | 2026-01-19 | Email | Hard Bid | 2026-01-01 | Email | Won | ✔ |  | 3845
Q-26-026 |  | Andersen | Meadowlark Place | 2026-01-23 | Email | Hard Bid | 01/23/2026 | Email | Sent |  | Healthcare | 89846
Q-26-027 |  | LMC | Meadowlark Place | 2026-01-27 | Bid Set | Hard Bid | 01/23/2026 | BuildingConnected | Sent |  | Healthcare | 89846
Q-26-028 |  | Viking | Legacy GS WHA Expansion | 2026-01-20 | Bid Set | Hard Bid | 01/20/2026 | Email | Sent |  | Healthcare | 86074
Q-26-029 |  | Viking | Legacy EMC Trauma Relocation | 2026-01-20 | 50% SD | Budget | 01/20/2026 | Email | Sent |  | Healthcare, Renovation | 65183
Q-26-030 |  | Cameron's Chok Dee | Pacific Towers Ste 1012 Revised Layout | 2026-01-20 | Bid Set | Hard Bid | 01/20/2026 | Email | Won | ✔ | Commercial | 9290
Q-26-031 |  | CCDC | 153 Volcano View- Cam's Casework | 2026-01-27 | Email | Design Assist | 02/06/2026 | Email | Sent |  |  | 4114
Q-26-032 |  | Inline | Pacific University Dining Cabs & CT | 2026-01-22 | Email | Hard Bid | 01/22/2026 | Email | Sent |  |  | 5125
Q-26-033 |  | Design Build | NW Urology Price 3 base Cabs | 2026-01-26 | Email |  | 01/26/2026 | Email | Sent |  | Healthcare | 1430
Q-26-034 |  | Five Star | Legacy Silverton Purple Casework | 2026-01-26 | Email | Hard Bid | 01/26/2026 | Email | Sent |  | Healthcare, Renovation | 4726
Q-26-035 |  | Trainor Construction | Design Within Reach | 2026-01-15 | Email | Hard Bid | 01/15/2026 | Email | Won | ✔ | TI, Commercial | 22923
February
Q-26-037 |  | Norwest | Clemons Oral Surgery | 2026-02-02 | Email | Hard Bid | 02/02/2026 | Procore | Client Lost |  | Dental | 102519 |  |  |  | We beat Gunderson
Q-26-038 | 01/22/2026 | Norwest | Legacy TOC OBGYN Expansion | 2026-02-02 | 100% DD | Hard Bid | 02/02/2026 | Procore | Sent |  | Healthcare, TI | 91705
Q-26-039 |  | Viking | Legacy TOC OBGYN Expansion | 2026-02-04 | 100% DD | Hard Bid | 02/02/2026 | Email | Sent |  | Healthcare, TI | 99349
Q-26-040 |  | Five Star | Legacy TOC OBGYN Expansion | 2026-02-05 | 100% DD | Hard Bid | 02/02/2026 | Email | Sent |  | Healthcare, TI | 99349
Q-26-041 | 01/27/2026 | Norwest | NW Windermere | 2026-02-06 | 100% DD | Budget | 01/29/2026 | Procore | Sent |  | Healthcare | 102814 |  |  |  | V1: Quartz and Veneer V2: Furniture ALTs V3: All P-Lam
Q-26-042 |  | Robert Hakes | Pacific Office Automation | 2026-02-06 | Email | Hard Bid | 02/06/2026 | Email | Won | ✔ |  | 8057
Q-26-043 |  | Norwest | TOC Plastic Surgery | 2026-02-10 | 100% SD | Budget | 02/09/2026 | Procore | Sent |  | Healthcare, Renovation, TI | 51640
Q-26-044 |  | CCDC | Park Tower 4- Suite 209 | 2026-02-09 | Bid Set | Hard Bid | 02/09/2026 | Email | Sent |  | Commercial, TI | 8454
Q-26-045 |  | PMB | Peacehealth Phys Pavilion Ste 100 | 2026-02-10 | Bid Set | Hard Bid | 02/10/2026 | Email | Sent |  |  | 9099
Q-26-046 | 11/19/2025 | Viking | Adventist Health 3rd Floor// Digestive Health | 2026-02-13 | 100% DD | Hard Bid | 02/13/2026 | Email | Sent |  | Healthcare | 280677
Q-26-047 |  | Jubitz | New Cabs | 2026-02-13 | Bid Set | Hard Bid | 02/07/2026 | Email | Won | ✔ | Commercial, Renovation | 5960
Q-26-048 |  | Robert Hakes | St Andrews Church RR | 2026-02-20 | Bid Set | Hard Bid |  | Email | Won | ✔ |  | 13731
Q-26-049 |  | Norwest | Eye health NW Admin Remodel | 2026-02-22 | 100% SD | Budget |  | Procore | Won | ✔ | Healthcare | 9340
Q-26-050 |  | Five Star | Emanuel Rm 5403 | 2026-02-11 | Email | Hard Bid |  | Email | Sent |  | Healthcare, Renovation, Hospital | 6024
Q-26-051 |  | Robert Hakes | Divine Complexion | 2026-02-11 | Email | Hard Bid | 02/11/2026 | Email | Sent |  | TI, Healthcare, Commercial | 14834
Q-26-052 |  | Norwest | ROSECITY HEAD & NECK SURGERY | 2026-02-06 | 100% SD | Hard Bid | 02/06/2026 | Email | Won | ✔ | Healthcare | 33285
Q-26-053 |  | Mackin's Auto | Office Remodel | 2026-02-13 | Email | Hard Bid | 02/13/2026 | Email | Won | ✔ |  | 4593
Q-26-054 |  | Five Star | Emanuel Countertop | 2026-02-16 | Email | Budget | 02/24/2026 | Email | Sent |  |  | 7990
Q-26-055 |  | Pacific Crest | Blue Ox | 2026-02-23 | Email | Hard Bid | 02/24/2026 | Email | Client Lost |  | Commercial, TI | 60849
Q-26-056 |  | Essex | D&T Excavation Shop | 2026-02-17 | Permit | Hard Bid | 02/16/2026 | Email | Sent |  | Commercial | 15945
Q-26-057 |  | Robert Hakes | Rhodes Chiropractic | 2026-02-13 | Email | Hard Bid | 02/13/2026 | Email | Sent |  | Healthcare, Renovation | 12412
Q-26-058 |  | LMHMC | Exam Rms | 2026-02-16 | Email | Hard Bid | 02/16/2026 | Email | Sent |  | Healthcare, Hospital, Renovation | 4968
Q-26-059 |  | LMHMC | PLAM Repairs | 2026-02-16 | Email | Hard Bid | 02/16/2026 | Email | Sent |  | Healthcare, Hospital, Renovation | 1150
Q-26-060 |  | Norwest | Skinwise Reception Desk | 2026-02-20 | Email | Design Assist |  | Email | Sent |  | Healthcare, Commercial | 14000
Q-26-061 |  | Robert Hakes | RHS- RS Medical | 2026-02-20 | Email | Hard Bid | 02/19/2026 | Email | Sent |  | Healthcare, Renovation | 9224
Q-26-062 |  | Andersen | Legacy SMC Outpatient Pharmacy | 2026-02-27 | Email | Hard Bid | 02/25/2026 | Email | Won | ✔ | Healthcare, Renovation | 36209
Q-26-063 |  | Robert Hakes | Westside Behavioral Therapy | 2026-02-27 | Email | Hard Bid | 02/26/2026 | Email | Sent |  | Healthcare | 23410
March
Q-26-065 | 03/01/2026 | Andersen | Prov St. Vincent CVL 7 | 2026-03-02 | CD | Hard Bid | 03/02/2026 | Email | Sent |  | Hospital, Renovation | 31283
Q-26-066 | 03/02/2026 | Pence | PeaceHealth Vancouver Rehab Hospital | 2026-03-10 | CD | Hard Bid | 03/11/2026 | ConstructConnect | Sent |  | Hospital | 709104
Q-26-067 | 03/03/2026 | Howard S Wright | PeaceHealth Vancouver Rehab Hospital | 2026-03-10 | CD | Hard Bid | 03/11/2026 | BuildingConnected | Sent |  | Hospital | 709104
Q-26-068 | 03/04/2026 | Andersen | PeaceHealth Vancouver Rehab Hospital | 2026-03-10 | CD | Hard Bid | 03/11/2026 | BuildingConnected | Sent |  | Hospital | 641981
Q-26-069 | 03/05/2026 | Inline | Pac U VOA East Family Relief Center | 2026-03-02 | Bid Set | Hard Bid |  |  | Sent |  |  | 9850
Q-26-070 | 03/06/2026 | Norwest | Livewell Animal Hospital - Skyview | 2025-03-11 | Bid Set | Hard Bid | 03/11/2026 | Procore | Client Backed Out |  |  | 139732
Q-26-071 | 03/07/2026 | Norwest | Livewell Animal Hospital - Tigard | 2026-03-03 | Bid Set | Hard Bid | 03/03/2026 | Procore | Client Backed Out |  | Vet, TI | 108196
Q-26-072 | 03/08/2026 | Robert Hakes | Eastside Ortho | 2026-03-04 | Bid Set | Hard Bid | 03/03/2026 | Email | Sent |  | Healthcare, TI | 87898
Q-26-073 | 03/09/2026 | Robert Hakes | Boulevard ALP | 2026-03-04 | Bid Set | Hard Bid | 03/04/2026 | Email | Sent |  | Healthcare | 6836
Q-26-074 | 03/10/2026 | LCL | LSC CT#1 Replacement | 2026-03-04 | Bid Set | Hard Bid | 03/04/2026 | BuildingConnected | Sent |  | Healthcare | 17485
Q-26-075 | 03/11/2026 | Mortenson | Kaiser WMC Gen Rad | 2026-03-03 | Bid Set | Hard Bid | 03/03/2026 | BuildingConnected | Sent |  | Healthcare, Hospital, Renovation | 5638
Q-26-076 | 03/12/2026 | Andersen | UO Acoustic Lab- Added Soffit and Cabs | 2026-03-04 | Permit | Hard Bid | 03/04/2026 | Email | Sent |  | School | 23822
Q-26-077 | 03/13/2026 | OHSU | Forest Grove PC Break RM | 2026-03-04 | Email | Hard Bid | 03/04/2026 | Email | Won | ✔ |  | 4681
Q-26-078 | 03/14/2026 | Norwest | Greenburg COR #2 - Private Office CT | 2026-03-09 | Email | Hard Bid | 03/09/2026 | Procore | Won | ✔ | Dental, Renovation | 1392
Q-26-079 | 03/15/2026 | First Cascade | Sandy City Hall | 2026-03-10 | Bid Set | Hard Bid | 03/10/2026 | BuildingConnected | Sent |  | Renovation | 16862
Q-26-080 | 03/16/2026 | Inline | PPS Cesar Chavez Window Sills | 2026-03-10 | Bid Set | Hard Bid | 03/10/2026 | BuildingConnected | Sent |  | School, Renovation | 16254
Q-26-081 | 03/17/2026 | Norwest | Laurelhurst Dental COR #3 | 2026-03-10 | Email | Change Order | 03/10/2026 | Email | Won | ✔ |  | 1002
Q-26-082 | 03/18/2026 | Norwest | Windermere Office Shelving Budget | 2026-03-10 | Email | Budget | 03/10/2026 | Email | Sent |  | Commercial, TI | 18904
Q-26-083 | 03/19/2026 | Robert Hakes | Therapeutic Associates Hazel Dell | 2026-03-13 | Email | Hard Bid | 03/11/2026 | Email | Sent |  | Healthcare, Renovation | 21447
Q-26-084 | 03/20/2026 | Inline | Office Remodel | 2026-03-16 | Email | Hard Bid | 03/11/2026 | Email | Won | ✔ | Commercial | 3895 |  |  |  | Owners Office-
Q-26-085 | 03/21/2026 | Five Star | Unity Lobby | 2026-03-11 | Email | Hard Bid | 03/11/2026 | Email | Won | ✔ | Healthcare | 157
Q-26-086 | 03/22/2026 | Five Star | LEH Room 2112 Casework | 2026-03-11 | Email | Re-Price | 03/11/2026 | Email | Sent |  | Healthcare | 1641
Q-26-087 | 03/23/2026 | Viking | LEMC Mob 2 Pharmacy | 2026-03-13 | Email | Budget | 03/12/2026 | Email | Sent |  | Hospital, Renovation | 70459
Q-26-088 | 03/24/2026 | Robert Hakes | Fischer Family Law | 2026-03-13 | Email | Hard Bid | 03/12/2026 | Email | Sent |  | Commercial, TI | 30973 |  |  |  | Notes to Bid: Remove Credenza & Storage Supply shelving. Revisit reception. Alt for Corian
Q-26-089 | 03/25/2026 | Andersen | HMC Lab Automation | 2026-03-16 | Email | Hard Bid | 03/16/2026 | Email | Sent |  | Healthcare | 1440
Q-26-090 | 03/26/2026 | Andersen | HMC- Nuclear Medicine | 2026-03-24 | CD | Hard Bid | 12/23/2025 | Email | Won | ✔ | Healthcare, Renovation | 55969 | https://andersencloud.egnyte.com/dl/yCPVrhMhqP7p
Q-26-091 | 03/27/2026 | Andersen | Corvallis Parks Maintenance | 2026-03-16 | Email | Hard Bid
Q-26-092 | 03/28/2026 | Schaffran | RLSB 1S050 Food Resource Center | 2026-03-16 | Email | Hard Bid | 03/13/2026 | Email | Won | ✔ | Healthcare, TI, Renovation | 17242
Q-26-093 | 03/29/2026 | Norwest | Gresham ASC - Oath | 2026-03-17 | Email | Hard Bid | 03/17/2026 | Email | Won | ✔ | Healthcare | 119973
Q-26-094 | 03/30/2026 | Norwest | Bling Dental Lab | 2026-03-17 | Email | Budget | 03/17/2026 | Email | Sent |  | Dental, Renovation | 18511
Q-26-095 | 03/31/2026 | CCDC | Ed Jones Lake Oswego | 2026-03-23 | Bid Set | Hard Bid | 03/23/2026 | Email | Sent |  | Commercial, TI | 5372
Q-26-096 | 04/01/2026 | Ross | FGSD Admin Office Remodel | 2026-03-23 | Email | Hard Bid | 03/24/2026 | BuildingConnected | Sent |  | School, TI | 5215
Q-26-097 | 04/02/2026 | Viking | OHSU CCB ITG & Rev Cycle Relocation | 2026-03-27 | 100% DD | Budget | 03/27/2026 | Email | Sent |  | Healthcare, Renovation, Hospital | 97932 |  |  |  | DD Bid. 12% Overhead contingency
Q-26-098 | 04/03/2026 | Willamette Falls | Nuc Med & Shelving | 2026-03-27 | Email | Hard Bid | 03/26/2026 | Email | Sent |  | Healthcare, Renovation | 801
Q-26-099 | 04/04/2026 | Five Star | LMHMC Suite 550 | 2026-03-20 | Email | Hard Bid | 03/20/2026 | Email | Pending |  | Healthcare, Renovation | 2300
Q-26-100 | 04/05/2026 | Norwest | Windermere Oak Shelves | 2026-03-24 | Email | Budget | 03/24/2026 | Email | Sent |  | Commercial | 23733
April
Q-26-102 |  | Robinson Construction | Ridgefield Community Center | 2026-04-01 | [8 empty] | https://securecc.smartinsight.co/#/PublicBidProject/846100
Q-26-103 |  | Viking | LEMC Pulmonary | 2026-04-03 | 100% DD | Budget | 2026-04-02 | Email | Sent |  |  | 109080
Q-26-104 |  | Andersen | HMC Healthplace Ortho & Rehab | 2026-04-03 | Email | Hard Bid | 2026-04-02 | Email | Sent |  |  | 54822
Q-26-105 |  | Norwest | Bling Dental Lab & PLAM Repairs | 2026-04-10 | Email | Budget | 03/17/2026 | Email | Sent |  | Dental, Renovation | 19859
Q-26-106 |  | Andersen | OSU HCIC ASI 22 | 2026-04-03 | Email | Hard Bid | 03/24/2026 | Email | Sent |  |  | 1632
Q-26-107 |  | Viking | HMC Healthplace Ortho & Rehab | 2026-04-01 | Email | Hard Bid | 04/01/2026 | Email | Sent |  | Hospital | 54822
Q-26-108 | 03/27/2026 | Bremik | Gray Courthouse Improvements | 2026-04-07 | Email | Hard Bid |  | ConstructConnect | Declined
Q-26-109 |  | Skyward Construction | OBH Express Care Clinic | 2026-04-10 |  |  |  |  | Declined
Q-26-110 |  | Robert Hakes | Five Below | 2026-04-02 |  |  |  |  | No Bid
Q-26-111 |  | Lease Crutcher Lewis | Finn Partners TI- Bend | 2026-04-06 | Bid Set | Hard Bid | 04/06/2026 | BuildingConnected | Sent |  | Commercial, TI | 48460
Q-26-112 |  | Norwest | EyeHealth NW- Lake Oswego | 2026-04-06 | Permit | Hard Bid | 04/06/2026 | Procore | Sent |  | TI, Commercial, Healthcare | 59291
Q-26-113 |  | Hakes | WFG-Coldwell Banker | 2026-04-08 | Bid Set | Hard Bid | 04/06/2026 | Email | Sent |  | Commercial, TI | 11948
Q-26-114 |  | Andersen | Prov St. Vincent CVL 7 | 2026-04-10 | CD | Hard Bid |  | Email | Sent |  | Hospital, Renovation | 33128
Q-26-115 |  | Pence | Goodwill Silverton | 2026-04-23 | Permit | Hard Bid |  | Email
Q-26-116 |  | Mortenson | Kaiser WMC Gen Rad | 2026-04-14 | CD | Hard Bid |  | BuildingConnected | Sent |  | Healthcare | 6109
Q-26-117 |  | Hakes | Los Pepes / Senior Taps | 2026-04-13 | Permit | Hard Bid |  | Email |  |  |  | 32951
Q-26-118 |  | Cameron's Chok Dee Contracting | Park Towers 1 Suite 120 Repairs | 2026-04-14 | Email | Hard Bid |  | Email | Sent |  |  | 741
Q-26-119 |  | Norwest | Archie's Playground | 2026-04-14 | CD | Hard Bid | 2026-04-14 | Procore | Sent |  | Dental, TI | 67984 |  |  |  | Updated 4/16/26
Q-26-120 | 10738 | Norwest | NW Windermere- CD Set | 2026-04-24 | CD | Hard Bid | 2026-04-20 | Procore | Sent |  | Commercial, TI | 118157
Q-26-121 |  | Norwest | Dr Saito | 2026-04-14 | DD | Budget | 2026-04-13 | Email | Sent |  | TI | 59539
Q-26-122 |  | Norwest | Dr Leung | 2026-04-14 | DD | Budget | 2026-04-13 | Email | Sent |  |  | 55217
Q-26-123 |  | Cameron's Chok Dee Contracting | Park Towers 5 Suite 110 | 2026-04-16 | CD | Hard Bid | 2026-04-15 | Email | Sent |  |  | 25351
Q-26-124 |  | Lorentz Bruun | OR State Credit Union TI (Cedar Mill) | 2026-04-17 | CD | Hard Bid | 2026-04-16 |  | Sent |  |  | 24077
Q-26-125 |  | Andersen | Vancouver Office TI | 2026-04-23 | Bid Set | Hard Bid |  | BuildingConnected |  |  | Commercial TI | 5771
Q-26-126 |  | Peacehealth Longviewk | OR Countertop Overlay | 2026-04-16 | Email | Budget | 2026-04-15 | Email | Sent |  | Healthcare | 6792
Q-26-127 |  | Peacehealth Longviewk | ACU 7 Desks/BHU 3rd Floor | 2026-04-16 | Email | Budget | 2026-04-15 |  | Sent |  |  | Options
Q-26-128 |  | Peacehealth Longview | E.D. Lounge | 2026-04-16 | Email | Budget |  |  | Sent |  |  | 7712
Q-26-129 |  | Peacehealth Longview | E.D. Admitting | 2026-04-16 | Email | Budget |  |  | Sent |  |  | 1755
Q-26-130 |  | Cameron's Chok Dee Contracting | Park Tower 3 Suite #220 | 2026-04-16 | Bid Set | Hard Bid | 2026-04-16 | Email | Sent |  |  | 10038
Q-26-131 |  | PeaceHealth Longview | Breakroom Countertop -Rm B68-02-2244 | 2026-04-20 | Email | Budget |  |  | Sent |  |  | 3141
Q-26-132 |  | PeaceHealth Longview | ACU Admitting- New Corian Overlay & Repair Self Edge | 2026-04-20 | Email | Budget |  |  | Sent |  |  | 15468
Q-26-133 |  | Providence Milwaukie | Behavioral Health- Cabs & CT Remodel | 2026-04-21 | Email | Hard Bid | 2026-04-21 |  | Sent |  |  | 4539
Q-26-134 |  | Viking | LH GS Path Lab Remodel | 2026-04-28 | SD | Budget
Q-26-135 |  | Thad Metzger | Daimlers Clinic | 2026-04-21 | Email | Hard Bid | 2026-04-21 |  | Sent |  | Commercial TI | 2108
Q-26-136 |  | Cameron's Chok Dee | PTAdd #170
Q-26-137
Q-26-138
Q-26-139
May
Q-26- |  | Perlo | MCPB MRI Replacement | 2026-05-05
June
July
August
September

## 2025 Bid Tracker
Job ID | Month | Client | Project Name | Bid Due Date | Drawing Stage | Bid Type | Sent Date | Sub. Method | Status | Win? | Job Type | Est. Bid Value | Link: Drawings | Link: Specs | Link: Schedule | Notes | Bid Feedback | NTP Received? | Final Cost | Profit Margin ($) | CO Link | Lessons Learned
May
Q-25-003 |  | Ross | Forest Grove HS Renovations | 05/15/2025 | Bid Set | Hard Bid | 05/15/2025 | Email | Sent |  | School | 53368
Q-25-004 |  | Andersen | UO Acoustic Research Lab | 05/21/2015 | Bid Set | Hard Bid | 05/21/2015 | Email | Sent |  | School | 19226
Q-25-005 |  | Robert Hakes | Coldwell Banker Bain Lake Oswego | 05/14/2025 |  | Design Assist | 05/14/2025 | Email | Sent |  | TI | Opt #1 $7649 / Opt #2 5367
Q-25-006 |  | Norwest | ZoomCare Progress Ridge | 05/16/2025 |  | Hard Bid | 05/16/2025 | Email | Sent |  | Healthcare, TI | 22134
Q-25-007 |  | Cornice | Harmony BLD1 & 2- Spec TI | 05/23/2025 |  | Hard Bid | 05/23/2025 | Email | Client Lost |  |  | 6984 |  |  |  |  | $1000 high | No
Q-25-008 |  | Robert Hakes | Therapeutic Associates 3 Room | 05/15/2025 |  | Budget | 05/15/2025 | Email | Sent |  | Healthcare, TI | 18814 |  |  |  | Sent Budget for Qtz (quod minui) & P-lam Deduct 5.15.25
Q-25-009 |  | Lease Crutcher Lewis | Legacy Salmon Creek CT Replacement | 05/29/2025 |  | Budget | 05/29/2025 | Email | Sent |  | Healthcare, Hospital | 8329
June
Q-25-011 |  | Lease Crutcher Lewis | PeaceHealth CMP Urology Renovation | 06/24/2024 | CD | Hard Bid | 06/04/2025 | Email | Declined |  | Healthcare, Renovation | 100268 | https://www.zztakeoff.com/app/takeoff?projectId=GamthffsBwLTgtDHo&pageId=iSohJaS4iSpkATZRJ , https://mylewis-my.sharepoint.com/personal/kagan_reardon_lewisbuilds_com/_layouts/15/onedrive.aspx?id=%2Fpersonal%2Fkagan%5Freardon%5Flewisbuilds%5Fcom%2FDocuments%2FDocuments%2F%5FPC25029%20%2D%20PEAC%20CMP%20UROLOGY%2FPC25029%20PEAC%20CMP%20UROLOGY%20%2D%20Drawings&ga=1 |  |  | Alt Accepted |  | Yes
Q-25-012 |  | Howard S Wright | Kaiser IRT HDR & CT Procedure Suite Expansion | 06/02/2024 |  |  | 06/02/2025 | Email | Sent |  | Healthcare, Hospital | 64694.8
Q-25-013 |  | Andersen | Legacy Emanuel Apothecary | 06/04/2025 |  | Budget | 06/04/2025 |  | Sent |  | Healthcare | 49667
Q-25-014 |  | Norwest | Willowbrook Vet | 06/10/2025 | Bid Set | Hard Bid | 06/10/2025 | Procore | On Hold |  | Vet | 27990
Q-25-015 |  | Robert Hakes | Beem Light Sauna- Install Only | 06/02/2025 | Permit | Install Only | 06/02/2025 | Email | Won | ✔ | TI, Healthcare | 895 |  |  | 09/19/2025 |  |  | Yes
Q-25-016 |  | Schaffran | PPMC Restroom Counters | 06/01/2025 |  |  | 06/01/2025 |  | Sent |  |  | 6724.76
Q-25-017 |  | Schaffran | PPMC Day Room Ice Machine | 06/01/2025 |  |  | 06/01/2025 |  | Sent |  |  | 496
Q-25-018 |  | Schaffran | PPMC Control Room Desk | 06/02/2025 |  |  | 06/02/2025 |  | Sent |  |  | 5330
Q-25-019 |  | Lease Crutcher Lewis | Legacy Salmon Creek MOB 2-Cardio | 06/27/2025 |  |  | 06/27/2025 | BuildingConnected | Sent |  |  | 90865 | https://app.buildingconnected.com/opportunities/683a24fe1ed47200532f624c/files
Q-25-020 |  | Cameron Chok-Dee | Oregon State Bar | 06/06/2025 |  |  | 06/06/2025 |  | Sent |  |  | 21178
Q-25-021 |  | Cameron Chok-Dee | Pacific BLDG TI | 06/06/2025 | Bid Set | Hard Bid | 06/06/2002 |  | Sent |  |  | 6886
Q-25-022 |  | Andersen | TV Camas- Phase 2 Budget | 06/17/2025 | 100% DD | Budget | 06/17/2025 | BuildingConnected | Sent |  |  | 371276
Q-25-023 |  | LSCMC | Family Birth Suite 407 | 06/18/2025 | Bid Set | Hard Bid | 06/18/2025 | Email | Won | ✔ | Hospital, Renovation | 16486 |  |  | Install 8/27/25
Q-25-024 |  | Essex | NWN PLNG Cabinets | 06/09/2025 |  |  | 06/09/2025 |  | Won | ✔ |  | 5443 | [5 empty] | Yes
Q-25-025 |  | Andersen | Providence PPP Ste 118 | 06/25/2025 | 50% SD | Budget | 06/25/2025 |  |  |  |  | 54168
Q-25-026 |  | Andersen | HMC Cath Lab 2 | 06/19/2025 | Bid Set | Hard Bid | 06/26/2025 | Email | Won | ✔ | Hospital, Renovation | 11862 | [5 empty] | Yes
Q-25-027 |  | Schaffran | OHSU School of Nursing 550 Classroom | 06/20/2025 | 50% SD | Budget | 06/20/2025 |  |  |  |  | 37713
Q-25-028 |  | Norwest | Archie's Playground | 06/25/2025 |  |  | 06/25/2025 |  |  |  |  | 59333
July
Q-25-030 | 06/27/2025 | Built Environments NW | Elephant's Deli-Supply/Install CT | 07/02/2015 | Bid Set | Hard Bid | 07/03/2025 | Email | Client Lost |  | Commercial, TI | 1180
Q-25-031 | 07/03/2025 | Pacific Premier Group | Fix and Move Reception Desk | 07/03/2025 | Bid Set | Hard Bid | 07/09/2025 | Email | Sent |  | Healthcare, Renovation | 1671
Q-25-032 | 07/01/2025 | Bremik | Eagle Industrial Equip. Warehouse | 07/09/2025 | Bid Set | Hard Bid | 07/07/2025 | Other | Sent |  | Commercial | 14205
Q-25-033 | 07/02/2025 | Centrex | Hangar Golf West Kitchen TI | 07/09/2025 | Bid Set | Hard Bid | 06/24/2025 | Email | Sent |  | Commercial | 15928 |  |  |  |  | 8/7 Follow up- Waiting on Client approval
Q-25-034 | 07/02/2025 | Centrex | Hangar Golf West RR TI | 07/09/2025 | Bid Set | Hard Bid | 07/05/2025 | Email | Sent |  | Commercial | 11663 |  |  |  |  | 8/7 Follow up- Waiting on Client approval
Q-25-035 | 07/02/2025 | Inline | Twin Oaks Plaza 101 Kitchenette | 07/09/2025 | Bid Set | Hard Bid | 06/28/2025 | Email | Sent |  | Commercial, TI | 7898
Q-25-036 | 07/11/2025 | JH Kelly | OCC Microwave Shelf | 07/11/2025 | Email | Hard Bid | 07/11/2025 | Email | Sent |  | Renovation | 721.45
Q-25-037 | 07/08/2025 | Andersen | Vancouver VA Dental | 07/11/2025 | CD | Hard Bid (Fab Only) | 07/10/2025 | Email | Sent |  | Healthcare, Dental, Renovation | 7861 | https://www.zztakeoff.com/app/takeoff?projectId=jmXtHDuNymN3cbeYh&pageId=i4kKnRGfeYNcBEaoG |  |  | Supply Only Bid
Q-25-038 | 07/10/2025 | Norwest | OSM Phase 2- Add Counter Storage Nook | 07/15/2025 | Bid Set | Hard Bid | 07/14/2025 | Procore | Won | ✔ | TI | 1696 | [5 empty] | Yes
Q-25-039 | 07/15/2025 | Norwest | Head and Neck Lovejoy | 07/15/2025 | Email | ROM | 07/15/2025 | Email | Sent |  | Healthcare | 77128 | https://www.zztakeoff.com/app/takeoff?projectId=hF8wHqMRTvXPCZCdM&pageId=Tojp3g3JEJ7aamMKc
Q-25-040 | 07/08/2025 | R&H Construction | KPFF-Vancouver TI | 07/16/2025 | 100% DD | Hard Bid | 07/15/2025 | BuildingConnected | Sent |  | TI, Commercial | 29897 | https://app.buildingconnected.com/opportunities/6862f5b51391b3009e9815c0/files
Q-25-041 | 07/07/2025 | Design+Build | NW Urology Tualatin | 07/16/2025 | 50% SD | Budget | 07/14/2025 | BuildingConnected | Sent |  | Healthcare | 105251.5 | https://app.buildingconnected.com/opportunities/6855e8d221009500372d4fd0/files
Q-25-042 | 07/09/2025 | Swinerton | Alaska Air-PDX Maintenance Hangar | 07/16/2025 | Bid Set | Hard Bid | 07/14/2025 | BuildingConnected | Sent |  | Commercial | 77216 | https://www.zztakeoff.com/app/takeoff?projectId=W4nEc8MKFEFSnquMu&pageId=uyhDWHkFp7dvtFcE2
Q-25-043 | 07/10/2025 | Viking E+C | LEMC Mob 2 2nd Fl Peds OS | 07/16/2025 | Permit | Hard Bid | 07/16/2025 | Email | Won | ✔ | Hospital, Renovation, Healthcare | 119319 | https://www.odrive.com/s/7ee37718-bca0-4e23-b8b2-93dbcfd454d3-68667633 |  |  | Add/Alt Pricing: Off Hrs Install |  | Yes
Q-25-044 | 07/08/2025 | LCL | Re-PriceLegacy Salmon Creek MOB 2-Cardio | 07/16/2025 | Bid Set | Re-Price |  |  | Declined |  | Healthcare, Renovation |  | https://app.buildingconnected.com/opportunities/683a24fe1ed47200532f624c/files
Q-25-045 | 07/07/2025 | Skanska | Redmond Municipal Airport ??? | 07/17/2025 | Bid Set | Hard Bid (Fab Only)
Q-25-046 | 07/11/2025 | Swinerton | Chicago Title TI | 07/21/2025 | Bid Set | Hard Bid | 07/21/2025 | BuildingConnected | Client Lost |  | TI, Commercial | 16950 | https://www.zztakeoff.com/app/takeoff?projectId=vxgpefthkQw3nrFFQ&pageId=CmyFEPEA5J5L5SCDz
Q-25-047 | 07/07/2025 | Built Environments NW | Centerpointe Drive Ste 410 | 07/22/2025 | Bid Set | Hard Bid | 07/22/2025 | Email | Sent |  | Commercial, TI | 9482 | https://www.zztakeoff.com/app/takeoff?projectId=6knvku4BbC5j3ySY6&pageId=8W3C5jBT48XiNZ6ie
Q-25-048 | 07/07/2025 | Built Environments NW | Centerpointe Drive Ste 430 | 07/22/2025 | Bid Set | Hard Bid | 07/23/2025 | Email | Sent |  | Commercial, TI | 4029 | https://www.zztakeoff.com/app/takeoff?projectId=6knvku4BbC5j3ySY6&pageId=8W3C5jBT48XiNZ6ie
Q-25-049 | 07/07/2025 | Built Environments NW | Centerpointe Drive Ste 580 | 07/22/2025 | Bid Set | Hard Bid | 07/24/2025 | Email | Sent |  | Commercial, TI | 9482 | https://www.zztakeoff.com/app/takeoff?projectId=6knvku4BbC5j3ySY6&pageId=8W3C5jBT48XiNZ6ie
Q-25-050 | 07/16/2025 | DD&C | Legacy Salmon Creek MOB 2-Cardio | 07/23/2025 | Bid Set | Hard Bid | 07/23/2025 | Email | Sent |  | Healthcare, Renovation | 61018.52
Q-25-051 | 07/25/2025 | Andersen | TVC CAMAS- SSM ALT | 07/28/2025 | Email | Budget |  | Email | Sent
Q-25-052 | 07/21/2025 | Norwest | Stones Family Dental | 07/29/2025 | Permit | Hard Bid | 07/29/2025 | Procore | Won | ✔ | Dental | 54923.97 | https://www.zztakeoff.com/app/takeoff?projectId=pAcEkQCBdfXP7RiwS&reportViewId=defaultMeasurementsGroupedByTakeoff&pageId=8ksGboqL3CucxJvRB |  |  |  |  | Yes
Q-25-053 | 07/25/2025 | JDL General Contractin | Terrain Coffee Shop | 07/30/2025 | Bid Set | Hard Bid |  |  | On Hold |  | TI, Commercial |  |  |  |  | Never Responded to materials RFI
Q-25-054 | 07/09/2025 | Andersen | HMC Ste 5300 Cardio/Vasc/Echo | TBD | CD | Hard Bid |  | Email |  |  | Healthcare, Renovation, Hospital |  | https://andersencloud.egnyte.com/fl/3WfXGtgxbVpG |  |  | Servo Pricing from Dave in Emails
August
Q-25-056 | 07/25/2025 | Aldrich | Salem Vet Clinic | 08/01/2025 | Bid Set | Hard Bid | 08/01/2025 | Email | On Hold |  | Vet, TI | 109514 | https://www.zztakeoff.com/app/takeoff?projectId=5BDb8zvbrhkbbfjjh&pageId=7gkvhqdXzLHxbELHg |  |  | Add/Alts: Several in email chain
Q-25-057 | 07/25/2025 | JDL General Contractin | Terrain Coffee Shop | 08/02/2025 | Bid Set | Hard Bid | 08/01/2025 | Email | On Hold |  | TI, Commercial | 65400 |  |  |  | Never Responded to materials RFI
Q-25-058 | 07/25/2025 | Design+Build | NW Urology Tualatin | 08/01/2025 | 75% DD | Budget | 08/01/2025 | BuildingConnected | Won | ✔ | Healthcare | 110813 | https://app.buildingconnected.com/opportunities/6855e8d221009500372d4fd0/files
Q-25-059 | 08/01/2025 | Howard S Wright | Kaiser AWL Core Line | 08/04/2025 | CD | Hard Bid | 08/04/2025 | Email | Sent |  | Healthcare | 24345.6 | https://www.zztakeoff.com/app/takeoff?projectId=d3ohf3ZDNjo3re4vX&pageId=cDL8f3TwoGcJCwHhD
Q-25-060 | 07/28/2025 | Andersen | Good Shepherd - Supply ONLY | 08/05/2025 | Permit | Hard Bid (Fab Only) | 08/05/2025 | BuildingConnected | Sent |  | Healthcare, Hospital | 180000 |  |  |  | Add/ALT P-Lam Window Sills- $2460
Q-25-061 | 08/01/2025 | Swinerton | One Financial 16th & 18th Floor TI | 08/05/2025 | CD | Hard Bid | 08/05/2025 | BuildingConnected | Sent |  | Commercial, TI | 17374 | https://www.zztakeoff.com/app/takeoff?projectId=wqpz28NZuwvj2KzJK&pageId=hnMwxoaptw8uYzmqb
Q-25-062 | 08/02/2025 | Cameron Chok-Dee | PT #210 | 08/06/2025 | Email | Hard Bid | 08/06/2025 | Email | Sent |  | Commercial, Renovation, TI | 3738.5 | No plan set
Q-25-063 | 08/05/2025 | Pence | Legacy MOB | 08/06/2025 | Email | Hard Bid | 08/07/2025 | Email | Sent |  | Healthcare, TI | 2085
Q-25-064 | 07/28/2025 | Andersen | POIC/RAAP Sunshine Campus | 08/06/2025 | 100% SD | Hard Bid (Fab Only) | 08/08/2025 | BuildingConnected | Sent |  | Commercial | 104388 |  |  |  | 8/19- Updated Assumptions per Phoenix email
Q-25-065 | 08/06/2025 | Andersen | CIC Change from lino to P-Lam | 08/07/2025 | Email | Re-Price | 08/11/2025 | Email | Sent |  | TI, School | 2267
Q-25-066 | 08/05/2025 | PeaceHealth | PeaceHealth Vancouver Coffee Bar | 08/08/2025 | Email | Hard Bid |  | Email |  |  |  | 2200
Q-25-067 | 08/12/2025 | Five Star | RCM Room 2878 | 08/12/2025 | Email | Hard Bid | 08/12/2025 | Email | Sent |  | Healthcare, Renovation | 850
Q-25-068 | 07/25/2025 | Andersen | Providence St Vincent CVL 4 | 08/12/2025 | CD | Hard Bid | 08/11/2025 | Email | Sent |  | Hospital, Healthcare, Renovation | 30388 | https://andersencloud.egnyte.com/fl/wJYk3qrr33kP
Q-25-069 | 07/12/2025 | Robert Hakes | Therapeutic Associates Misty Drive | 08/13/2025 | Email | Hard Bid | 08/13/2025 | Email | Won | ✔ | Healthcare, TI | 36059
Q-25-070 | 08/04/2025 | Willamette Falls MC | Pediatric Sink Surrounds | 08/12/2025 | Email | Hard Bid | 08/12/2025 | Email | Won | ✔ | Healthcare, Hospital, Renovation | 14812 | [5 empty] | Yes
Q-25-071 | 07/31/2025 | Lease Crutcher Lewis | Good Shepherd | 08/13/2025 | Permit | Hard Bid | 08/12/2025 | BuildingConnected | Sent |  | Healthcare, Hospital, TI | 241437
Q-25-072 | 08/08/2025 | Norwest | TOC Path Lab Option A | 08/14/2025 | Email | Hard Bid | 08/12/2025 | Email | Sent |  | Healthcare, Renovation | 986 |  |  |  | Add/Alt- $3582 for SS Floating CT
Q-25-073 | 08/04/2025 | Norwest | Zoom Care Mill Plain | 08/18/2025 | Bid Set | Hard Bid | 08/18/2025 | Procore | Client Lost |  | Healthcare, TI | 31423
Q-25-074 | 07/09/2025 | Andersen | HMC Ste 5300 Cardio/Vasc/Echo | 08/20/2025 | CD | Hard Bid | 08/20/2025 | Email | Won | ✔ | Healthcare, Renovation, Hospital | 83307 | https://andersencloud.egnyte.com/fl/3WfXGtgxbVpG |  | file:///C:/Users/evan/Downloads/HMC%20-%207th%20Ave-%20Medical%20Plaza%20Suite%205300%20TI%2008-01-2025%20Conformed%20set.pdf | Servo Pricing from Dave in Emails
Q-25-075 | 08/19/2025 | Andersen | TV Camas- Phase 2 | 08/21/2025 | 75% CD | Hard Bid |  | BuildingConnected | Pending |  |  | 398750
Q-25-076 | 08/17/2025 | JDL General Contractin | 205 Business Center- Kitchenette TI | 08/21/2025 | Bid Set | Hard Bid | 08/20/2025 | Email | Sent |  | Commercial, TI | 1810
Q-25-077 | 08/07/2025 | T.J. Nisbet | T.J. Nisbet Construction Office | 08/21/2025 | 50% SD | Budget |  | BuildingConnected |  |  | Commercial, TI | 42000
Q-25-078 | 08/11/2025 | R & H Construction | Head and Neck Lovejoy | 08/22/2025 | Email | Budget | 08/22/2025 | BuildingConnected | Sent |  | Healthcare | 111377 | https://www.zztakeoff.com/app/takeoff?projectId=hF8wHqMRTvXPCZCdM&pageId=Tojp3g3JEJ7aamMKc
Q-25-079 | 08/18/2025 | Cameron Chok-Dee | Pacific BLDG TI - Suite 1012 | 08/22/2025 | Email | Hard Bid | 08/22/2025 | Email | Sent |  | Commercial, TI | 5091
Q-25-080 | 07/07/2025 | Design+Build | NW Urology Tualatin | 08/25/2025 | Bid Set | Hard Bid | 08/25/2025 | BuildingConnected | Sent |  | Healthcare | 115381 | https://app.buildingconnected.com/opportunities/6855e8d221009500372d4fd0/files
Q-25-081 | 08/12/2025 | Lorentz Bruun | Oregon State Credit Union Remodel | 08/25/2025 | Bid Set | Hard Bid | 08/25/2025 | Email | Sent |  | Renovation | 10831.2 | https://www.lbruun.com/subcontractor/projects-bidding/oregon-state-credit-union-remodel---project-currently-bidding/
Q-25-082 |  | P&C Construction | Hillcrest Behavioral Health Campus | 08/26/2025 | Permit | Hard Bid |  | BuildingConnected |  |  | Healthcare
Q-25-083 | 08/15/2025 | Andersen | HMC Suite 5200 | 08/26/2025 | Bid Set | Hard Bid (Fab Only) | 08/26/2025 | Email | Won | ✔ | Healthcare | 394
Q-25-084 | 08/24/2025 | Robert Hakes | Coldwell Banker Lake Oswego OPT 4 | 08/26/2025 | Bid Set | Hard Bid | 08/26/2025 | Email | Sent |  | Commercial, TI | 5590
Q-25-085 | 08/05/2025 | Kramer Construction | Urban Air Adventure Park | 08/27/2025 | Permit | Hard Bid |  | BuildingConnected |  |  | Commercial, TI
Q-25-086 | 08/19/2025 | First Cascade | Marion County Health Building Remodel | 08/28/2025 | Bid Set | Hard Bid |  | BuildingConnected
Q-25-087 | 08/19/2025 | Andersen | UO Acoustic Research Lab | 08/29/2025 | Bid Set | Re-Price | 08/19/2025 | Email | Sent |  | School | 19226 |  |  |  | 8/19- 95% CD released- No change to scope
September
Q-25-089 | 08/27/2025 | Andersen | Springfield Quad Remodel | 09/02/2025 | 50% DD | Budget | 09/02/2025 | BuildingConnected |  |  |  | 95562
Q-25-090 | 09/02/2025 | Cameron Chok-Dee | Park Tower 2 Ste 190 | 09/03/2025 | Email | Hard Bid
Q-25-091 |  | Cameron Chok-Dee | 2321 Sunset Drive | 09/03/2025 | Email | Hard Bid
Q-25-092 | 08/26/2025 | Built Environments | Centerpointe Drive | 09/09/2025 | Bid Set | Hard Bid
Q-25-093 | 08/25/2025 | First Cascade | Center for Deaf & Hard of Hearing | 09/08/2025 | Permit |  |  | BuildingConnected
Q-25-094 | 09/01/2025 | Design Build | Milestone | 09/09/2025 | 75% DD | Budget | 09/08/2025 | BuildingConnected | Sent |  | Commercial, Renovation, TI | 30356
Q-25-095 | 08/25/2025 | Triplett Wellman | Center for Deaf & Hard of Hearing | 09/09/2025 | Permit |  |  | BuildingConnected
Q-25-096 | 08/26/2025 | Swinerton | Alaska Air-PDX Maintenance Hangar | 09/12/2025 | Bid Set | Re-Price |  | BuildingConnected | Sent |  | Commercial |  | https://www.zztakeoff.com/app/takeoff?projectId=W4nEc8MKFEFSnquMu&pageId=uyhDWHkFp7dvtFcE2
Q-25-097 | 08/28/2025 | Andersen | Charles Schwab Slabtown TI | 09/22/2025 | Bid Set |  |  | BuildingConnected
Q-25-098 | 08/29/2025 | James E John | Charles Schwab Slabtown TI | 09/24/2025 | Bid Set
Q-25-099 | 09/10/2025 | Andersen | Corvallis Parks Maintenance Facilities | 09/16/2025 | 100% DD | Budget
Q-25-100 |  | Cameron Chok-Dee | Ed Jones TI | 09/12/2025 | Bid Set
Q-25-101 | 08/04/2025 | Norwest | Zoom Care Mill Plain | 09/18/2025 | Bid Set | Hard Bid | 08/18/2025 | Procore | Sent |  | Healthcare, TI | 31423
Q-25-102 | 09/10/2025 | Redfern | WMBA Dispatch Hall | 09/24/2025 | CD | Hard Bid |  | Email
Q-25-103 | 09/15/2025 | Norwest | Geisler Oral Surgery | 09/17/2025
Q-25-104 | 09/15/2025 | Andersen | Providence PPP Ste 118 | 09/23/2025 | CD | Budget | 06/25/2025 |  |  |  |  | 54168 | https://andersencloud.egnyte.com/fl/dQ8Kw9KhHg8r
Q-25-105 | 09/18/2025 | Viking | LMG Ridgefield Buildout | 09/19/2025 | 100% DD | Budget
October
Q-25-107 | 10/06/2025 | Legacy Mt Hood | Retro Fit Tack Panel - Updated Proposal | 10/06/2025 | Email | Hard Bid | 10/06/2025 | Email | Won | ✔ | Healthcare | 3425
Q-25-108 | 10/06/2025 | Legacy Salmon Creek | Post Op 4th Floor Countertop Replacement | 10/06/2025 | Email | Hard Bid | 10/06/2025 | Email | Sent |  | Healthcare | 9337
Q-25-109 | 10/07/2025 | Norwest | Oregon Vascular Specialist Expansion | 10/06/2025 | 50% DD | Budget | 10/06/2028 | Email | Sent |  | Healthcare | 56788 | https://www.zztakeoff.com/app/takeoff?projectId=72DQSipwWzALz7K7i&pageId=HYr84TuZHLH9pmzBJ
Q-25-110 | 10/07/2025 | Andersen | Providence St Vincent iMRI Replacement | 10/01/2025 | 100% SD | Budget | 10/07/2025 | Email | Sent |  | Healthcare | 9479
Q-25-111 | 10/07/2025 | LCL | PCC CT Swing Spaces - SCB, TCB Classroom | 10/08/2025
Q-25-112 | 10/07/2025 | Andersen | PPMC- Behavioral Health Office Remodel | 10/08/2025 | Email | Hard Bid |  | Email | Won | ✔ |  | 31852
Q-25-113 | 10/07/2025 | BCCM Construction | Ivybrook Academy | 10/17/2025 | Bid Set | Hard Bid
Q-25-114 | 10/07/2025 | Andersen | TVC Camas 100% CD | 10/15/2025 | CD | Hard Bid |  |  | Sent |  | Hospital | 529510
Q-25-115 | 10/08/2025 | Inline | Chase Bank University Park TI | 10/22/2025
Q-25-116 | 10/08/2025 | OHSU HMC | 1321 Sink | 10/08/2025 | Email | Hard Bid | 10/09/2025 | Email | Sent |  | Healthcare | 17046
Q-25-117 | 10/10/2025 | Swinerton | PeaceHealth SPEC CT Rolling Cart | 10/14/2025 | Email | Hard Bid | 10/10/2025 | Email | Sent |  | Healthcare | 2659
Q-25-118 | 10/10/2025 | Norwest | Oath- Gresham ASC | 10/27/2025 | 100% DD | Budget | 10/28/2025 | Email | Sent |  | Healthcare | 138686 |  |  |  | Lots of Alts
Q-25-119 | 10/01/2025 | Deacon | CBRE Liberty Tower TIs | 10/17/2025 | Bid Set
Q-25-120 | 10/14/2025 | First Cascade | Rockwood Community Health | 10/28/2025 |  |  |  | BuildingConnected
Q-25-121 | 10/14/2025 | Cedar Mill Construction | Rockwood Community Health | 10/30/2025
Q-25-122 | 10/14/2025 | Inline | Rockwood Community Health | 10/20/2025
Q-25-123 | 10/15/2025 | Norwest | Eye Health NW - Aloha Clinic | 10/28/2025
Q-25-124 | 10/15/2025 | Robert Hakes | Coldwell Banker-Final Option(dont bid again) |  | Email | Hard Bid |  |  | Won | ✔ |  | 6977
Q-25-125 | 10/15/2025 | Norwest | Greenburg Pediatric Dentistry |  | Email | Hard Bid |  |  | Won | ✔ |  | 19264
Q-25-126 | 10/15/2025 | Powells | Powells PDX | 10/24/2025 | Bid Set | Hard Bid (Fab Only) | 10/21/2025 | Email | Won | ✔ | TI | 62757
Q-25-127 | 10/07/2025 | Norwest | ROC Orthopedic | 10/20/2025 | 100% SD | Budget | 10/20/2025 | Email | Client Lost |  | Healthcare | 313858
Q-25-128 | 10/30/2025 | Norwest | Sherwood High | 10/31/2005 | Email | Budget | 10/31/2025 | Email | Sent |  | School | 16036
Q-25-129 | 10/27/2025 | Robert Hakes | RHC- 701 Columbia Street | 10/30/2025 | Email | Budget | 10/30/2025 | Email | Sent |  | TI | 12165
November
Q-25-131 | 10/30/2025 | Ross | City Of Vancouver-Public Service Center 2nd Floor | 12/09/2025 | Bid Set | Hard Bid |  | BuildingConnected | Declined
Q-25-132 | 10/16/2025 | Andersen | Chehalis Casino | 11/14/2025 | Permit | Hard Bid |  | BuildingConnected | Declined |  | Commercial
Q-25-133 | 11/03/2025 | Inline | Troutdale WPFC Admin Remodel | 11/12/2025 | Bid Set | Hard Bid |  | BuildingConnected
Q-25-134 | 11/03/2024 | Norwest | Eye Health NW- Admin Remodel | 11/12/2025 | 100% SD | Budget |  | Procore | Sent |  | Renovation, Healthcare | 2482
Q-25-135 | 11/03/2025 | Deacon | Montgomery Park Ste 410 | 11/11/2025 | Bid Set | Hard Bid |  | BuildingConnected |  |  | Commercial, Renovation
Q-25-136 | 11/06/2025 | Robert Hakes | Orchard Market Center | 11/10/2025 | Bid Set | Hard Bid |  | Email |  |  |  | 16028
Q-25-137 | 11/06/2025 | LCL | Legacy Salmon Creek- CT 1 Replacement | 11/10/2025 | 75% CD | Hard Bid | 11/10/2025 | BuildingConnected | Sent |  | Hospital, Healthcare, Renovation | 19089
Q-25-138 | 11/06/2025 | Norwest | NW Windermere | 11/07/2025 | Bid Set | Hard Bid | 11/07/2025 | Email | Sent |  |  | 206000 |  |  |  | V1: Quartz and Veneer V2: Furniture ALTs V3: All P-Lam
Q-25-139 | 11/11/2025 | Andersen | The Bible Project | 11/18/2025
Q-25-140 | 11/13/2025 | Essex | Hillsboro Airport- Countertop | 11/13/2025 | Email | Hard Bid | 11/13/2025 | Email | Sent |  |  | 787
Q-25-141 | 11/07/2025 | Oregon Restoration | Courtyard @ Tabor | 11/12/2025 | Email | Hard Bid | 11/12/2025 | Email | Sent |  |  | 845
Q-25-142 | 11/07/2025 | Oregon Restoration | Bend-Hilton | 11/12/2025 | Email | Hard Bid | 11/12/2025 | Email | Sent |  |  | 290
Q-25-143 | 11/07/2025 | Oregon Restoration | Legacy Good Sam Path Cabs | 11/12/2025 | Email | Hard Bid | 11/12/2025 | Email | Sent |  |  | 4584
Q-25-144 | 11/17/2025 | DW Sivers | Airport Plaza Suite 205 Kitchen | 11/18/2025 | Email | Hard Bid | 11/17/2025 | Email | Sent |  | TI, Commercial | 3382
Q-25-145 | 11/14/2025 | OHSU HMC | Lab Automation Countertop | 11/14/2025 | Email | Hard Bid | 11/14/2025 | Email | Sent |  | Healthcare | 626
Q-25-146 | 11/07/2025 | Oregon Restoration | Legacy Good Sam Coffee Bar CT | 11/12/2025 | Email | Hard Bid | 11/12/2025 | Email | Sent |  | Healthcare | 2829
Q-25-147 | 11/12/2025 | Schaffran | OHSU Doernbecher Childrens | 11/17/2025 | Email | Hard Bid | 11/17/2025 | Email | Sent |  | Hospital, Renovation | 7687
Q-25-148 | 11/18/2025 | Viking | Legacy Ridgefield | 11/22/2025 | CD | Hard Bid | 11/24/2025 | Email | Sent |  | Healthcare | 191156
Q-25-149 | 11/19/2025 | Viking | Adventist Health 3rd Floor// Digestive Health | 11/24/2025 | 75% DD | Budget | 12/01/2025 | Email | Sent |  | Healthcare | 268870
Q-25-150 | 11/20/2025 | Norwest | Center for Dermatology & Laser Surgery | 11/24/2025 | 100% SD | Budget | 11/24/2025 | Email |  |  |  | 66371
Q-25-151 | 11/20/2025 | DD&C | PDX Juliett | 11/30/2025 | Email | Hard Bid
December
Q-25-153 | 11/18/2025 | Skanska | Legacy Health BH Clinic | 12/03/2025 | Permit | Hard Bid | 12/04/2025 | BuildingConnected | Sent |  | Renovation, Hospital | 143912.5 |  | Legacy BH Clinic Proposal |  |  | Went with our Number.
Q-25-154 | 11/25/2025 | Norwest | TOC Path Lab Remodel | 12/12/2025 | Bid Set | Hard Bid | 12/15/2025 | Procore | Won | ✔ |  | 3504
Q-25-155 | 11/25/2025 | Andersen | St Charles Inpatient Rehab | 12/10/2025 | Permit | Hard Bid (Fab Only) | 12/10/2025 | BuildingConnected | Sent |  | Healthcare | 375940 |  | ACC_StCharles_InpatientRehab_Proposal Worksheet.pdf
Q-25-156 | 11/25/2025 | Lease Crutcher Lewis | St Charles Inpatient Rehab | 12/10/2025 | Permit | Hard Bid (Fab Only) | 12/10/2025 | BuildingConnected | Lost |  | Healthcare | 375940
Q-25-157 | 12/08/2025 | Mortensen | St Charles Inpatient Rehab | 12/15/2025 | Permit | Hard Bid (Fab Only) | 12/10/2025 | BuildingConnected | Sent |  | Healthcare | 375940
Q-25-158 | 12/04/2025 | Norwest | Capital Surgery Center | 12/16/2025 | Permit |  | 12/16/2025 | Procore | Sent |  | Healthcare | 125813 |  | Nor_CapSurgery_Budget12.25.pdf
Q-25-159 | 12/01/2025 | Abbott | Graybar Electric Portland - New PWOR Branch | 12/19/2025 | Permit | Hard Bid | 12/18/2025 | BuildingConnected | Sent |  | Commercial | 16426 |  | Quartz Proposal from Jeremy
Q-25-160 | 12/01/2025 | Andersen | PNMC X-Ray Replacement | 12/02/2025 | Email | Hard Bid | 12/02/2025 | Email | Sent |  | Hospital, Renovation | 1207
Q-25-161 | 12/03/2025 | Robert Hakes | Fischer Family Law | 12/10/2025 | Email | Hard Bid | 12/10/2025 | Email | Sent |  | Renovation, TI, Commercial | 52949
Q-25-162 | 11/18/2025 | Providence | Providence Seaside | 12/04/2025 | Email | Hard Bid | 12/04/2025 | Email |  |  |  | 3233
Q-25-163 | 12/03/2025 | Viking | Legacy TOC OBGYN Expansion | 12/11/2025 | 100% DD | Hard Bid |  | Email | Sent |  |  | 94905
Q-25-164 | 12/08/2025 | Andersen | HMC- Nuclear Medicine | 12/24/2025 | 100% DD | Budget | 12/23/2025 | Email | Won | ✔ | Healthcare, Renovation | 55969 | https://andersencloud.egnyte.com/dl/yCPVrhMhqP7p
Q-25-165 | 12/08/2025 | JH Kelly | Ice Maker Cabinet | 12/12/2025 | Email | Hard Bid |  | Email | Sent |  | Renovation | 590
Q-25-166 | 12/08/2025 | 4th Ave Homes | PCC Remodel Phase 2 | 12/10/2025 | Email | Hard Bid | 12/10/2025 | Email | Sent |  |  | 73592
Q-25-167 | 11/24/2025 | Andersen | Legacy Unity ECT 4th Floor | 12/08/2025 | Permit | Hard Bid (Fab Only) | 12/08/2025 | BuildingConnected | Sent |  | Hospital, Renovation | 166210
Q-25-168 | 188408 | Andersen | Providence Newberg MOB | 12/22/2025 | 100% DD | Budget |  | Email | Sent |  | Healthcare, Renovation | 188408
Q-25-169 | 12/09/2025 | Five Star | Emmanuel RCH 5827 | 12/12/2025 | Email | Hard Bid |  | Email | Sent |  |  | 4989
Q-25-170 | 12/09/2025 | Robert Hakes | St Andrew Lutheran Church | 12/12/2025 | Email | Hard Bid | 12/12/2025 | Email | Sent |  | Renovation | 10131 |  | https://formstructure-my.sharepoint.com/:x:/g/personal/evan_formandstructure_net/IQAosg000aUpTIWx-ymVxHiaAeIGP14v6TCosciPf5EGIUA?e=cz3gtf
Q-25-171 | 12/10/2025 | Lease Crutcher Lewis | Legacy Salmon Creek-OBS | 12/23/2025 | 100% DD | Budget | [5 empty] | 274100
Q-25-172 | 12/03/2025 | Andersen | PPMC 5R Bariatric RR & Shower | 12/16/2025 | Email | Budget |  | Email | Sent |  | Healthcare, Renovation | 3638
Q-25-173 | 12/11/2025 | Deacon | Charles Schwab LO TI | 01/02/2026 | Bid Set | Hard Bid | 12/12/2025 | BuildingConnected | Sent |  | Commercial, TI | 13351 |  | Deacon_SchwabLO_Proposal12.25.pdf
Q-25-174 | 12/12/2025 | Lease Crutcher Lewis | Providence Newberg- Womens Health Expansion | 01/05/2026 | 100% DD | Budget | 12/23/2025 | BuildingConnected | Sent |  | Healthcare | 188408
Q-25-175 | 12/12/2025 | PRoviidence WF | Providence Willammette Falls- Ped Sink Surround | 12/15/2025 | Email | Hard Bid | 12/15/2025 | Email | Sent |  | Hospital, TI | 2696
Q-25-176 | 12/15/2025 | Bremik | Charles Schwab Lake Oswego TI | 12/15/2025 | Bid Set | Hard Bid | 12/15/2025 | ConstructConnect | Sent |  | Commercial, TI | 13351
Q-25-177 | 12/15/2025 | JE John | Charles Schwab Lake Oswego TI | 12/29/2025 | Bid Set | Hard Bid | 12/17/2025 | Email | Sent |  | Commercial, TI | 13351
Q-25-178 | 12/15/2025 | Pence | Legacy Good Sam Mob 3 NW Gastro | 12/23/2025 | [7 empty] | 132741
Q-25-179 | 12/16/2025 | R&H | Trillium- Phase 2 | 01/06/2026 | 100% SD | Budget |  | BuildingConnected
Q-25-180 | 12/16/2025 | Andersen | UO Acoustic Research Lab | 01/05/2026 | CD | Hard Bid | [5 empty] | 19226
Q-25-181 | 12/18/2025 | Viking | Good Sam Urology Mob 1 | 12/24/2025 | 50% DD | Budget |  | Email |  |  |  | 33173 |  | Viking_GoodSamUro_Budget12.25.pdf
Q-25-182 | 12/18/2025 | Swinerton | Campbell Global-JPMC Conversion | 12/30/2025 | CD | Hard Bid |  | BuildingConnected
Q-25-183 | 12/18/2025 | Norwest | Oregon Vascular Specialist Expansion | 01/07/2026 | CD | Budget |  | Procore | Won | ✔ | Healthcare | 55575 | https://www.zztakeoff.com/app/takeoff?projectId=72DQSipwWzALz7K7i&pageId=HYr84TuZHLH9pmzBJ
Q-25-184 | 12/18/2025 | Norwest | NW Eye Clinic- Lake Oswego | 12/29/2025 | 100% SD | Budget
Q-25-185 | 12/15/2025 | DD&C | Go To Ortho | 12/30/2025 |  |  |  | Email
Q-25-186 | 12/23/2025 | DD&C | Bridgeport Service Request
Q-25-187 | 12/23/2025 | CCDC | Park Tower 2 Ste 170 | 12/30/2025 | Email | Budget |  | Email | Sent |  |  | 3263
Q-25-188 | 12/23/2025 | Robert Hakes | Oak Grove Therapeutic Associates

## Current Jobs
Job # | PM | Client | Project | Contract ($) | Appvd COs ($) | Curr. Contract ($) | Bid Ref | Fab Status | Install Date | Install Status | Invoice Status | Notes
001 | G | — | MT. TABOR KITCHEN |  | 0
002 | P | NIC RAMIREZ | DOORS | 1600 | 0 | 1600
003 | G | ACC / PPMC | C.TOPS | 5302 | 0 | 5302
004 | G | OHSU HMC | 8 AUD C.SINKS | 1100 | 0 | 1100
005 | G | LMHMC | RADIATION ONCOLOGY REM. DRAWERS | 450 | 0 | 450
006 | G | OHSU HMC | NEW TABLETOP | 643 | 0 | 643
007 | G | COATS & TAILS | LOBBY / MISC | 3920 | 0 | 3920
008 | P | UNIV. ACH. MILLWORK | HILLS. CAMPUS | 3688 | 0 | 3688
009 | G | OHSU HMC | P/L COUNTERTOP | 1180 | 0 | 1180
010 | P | MANION DESIGN LLC | BASE CAB'S W/C | 2325.2 | 0 | 2325.2
011 | G | VIKING | LGS MOB 2 OP PHARMACY | 47988 | 0 | 47988 | Q-26-003
012 | G | NORWEST | OR VASC. SPECIALISTS | 55575 | 0 | 55575
013 | G | NORTHWEST PRIMARY CARE | KITCHEN | 7183 | 0 | 7183
014 | J | LSCMC | 527 CLOSET | VOID | [7 empty] | VOID - crossed out on original job list
015 | G | JESUIT HS | CT & SHELVES | 589.95 | 0 | 589.95
016 | G | JOHN | MDF CIRCLES |  | 0
017 | G | JOHN | PLYWOOD PANELS |  | 0
018 | G | LMHMC | MOB 2 STE 200 | 6118 | 0 | 6118
019 | G | OREGON RESTORATION | VANITY | 1074 | 0 | 1074
020 | P | MARK HORYAT | MISC |  | 0
021 | G | NORWEST | TOC LAB REMODEL | 3504 | 0 | 3504
022 | G | 5 STAR | EMANUAL RM 5400 CASEWORK | 5713 | 0 | 5713
023 | P | JOHN HOLTMANN | GOLF CABINET |  | 0
024 | G | CCDC | VOLCANO VIEW BOOKCASES | 4114 | 0 | 4114
025 | G | SCHAFFRON CONST | 2 DOORS |  | 0
026 | G | ESSEX | BONNEVILLE ST JOHNS | 3845 | 0 | 3845
027 | G | LMHMC | MATERNITY CAB | 1973 | 0 | 1973
028 | G | CCDC | PACIFIC BLD SUITE 1012-1015 | 9296 | 0 | 9296
029 | G | TRAINOR COMMERCIAL CONST. | DESIGN WITHIN REACH | 22923 | 0 | 22923 | Q-26-035
030 | J | R. HAKES | PACIFIC OFFICE AUTOMATION RENO | 6657 | 0 | 6657 | Q-26-043
031 | J | R. HAKES | ST. ANDREWS CHURCH DR | 13731 | 0 | 13731
032 | G | LMHMC | FIV CABIN |  | 0
033 | G | 5 STAR | UNITY LOBBY DRAWER BOX | 157.5 | 0 | 157.5
034 | G | INLINE | OFFICE REMODEL | 4955 | 0 | 4955 | Q-26-086
035 | G | BEAVERTON DENTAL | MISC |  | 0
036 | G | ACC / PROV. GATEWAY | MOB X-RAY | 1746 | 0 | 1746
037 | G | AWE | CUT PARTS | 200 | 0 | 200
038 | G | LOIS | G. TOP |  | 0
039 | G | ALOFT | REFINISH DOOR |  | 0
040 | G | FOREST GROVE | BREAK RM | 4681 | 0 | 4681
041 | G | 5 STAR | LEMC MOB 2 STE 550 | 2300 | 0 | 2300
042 | G | ACC / LSMC | OP PHARMACY | 36209 | 0 | 36209
043 | G | JEFF RULE | DOOR REPAIR |  | 0
044 | P | MARK ASPLUND | CASEWORK | T+M |  | T+M
045 | G | LMHMC | STAFF LOUNGE | 3019 | 0 | 3019
046 | G | NORWEST | ROSECITY HEAD & NECK SURGERY | 26942 | 0 | 26942
047
048
049
050
051
052
053
054
055
056
057
058
059
060
061
062
063
064
PM Color Key:
G
P
J

## Change Order
CO # | Job ID | Client | Project Name | CO Description | Date Submitted | Amount ($) | Status | Approved Date | Notes
CO-26-001-01 | Q-26-003 | Viking | Legacy Good Sam Pharmacy Retrofit | Owner-directed scope addition — additional upper cabs Room 112 |  | 2400 | Pending
CO-26-062-01 | Q-26-062 | Andersen | LSMC OP Pharmacy | ASI-01 - Add Full Height Cab with Lock, Pick-up windown shelving | 2026-04-20 | 2178 | Pending
CO # format: CO-YY-JJJ-NN (e.g. CO-26-003-01 = 2026, Job Q-26-003, CO #1)

## Historical
Year | Total Bids | Submitted | Won | Win Rate | Total Won Value ($) | Avg Bid Value ($) | Notes
2024 |  |  |  | 0% | 1861816 |  | Full year revenue — manually recorded
2025 | 143 | 93 | 17 | 18.28% | 331875.97 | 19522.1159 | 2025 partial as of 9/4/25: $1,924,157 revenue. Powells PDX, Oregon Vascular, Greenburg Pediatric moved to 2026.
2026 | 108 | 91 | 24 | 26.37% | 549952 | 22914.6667 | Year in progress. Includes Powells PDX, Oregon Vascular, Greenburg Pediatric, TOC Path Lab from 2025 tracker (2026 revenue).

## Dashboard
Estimating Dashboard — 2026 YTD vs 2025
Metric | 2026 (YTD) | 2025 (Full Year) | Notes
Total Bids Logged | 131 | 178
Bids Submitted | 113 | 115
Bids Won | 25 | 20
Win Rate | 22.12% | 17.39% | Won ÷ Submitted
Total Won Value ($) | 418192 | 695332.97
Avg Won Bid Value ($) | 16727.68 | 34766.6485 | Won Value ÷ Won Count
Avg Est. Bid Size ($) | 47193.3361 | 62148.8599 | Avg across all logged bids
Active Jobs (Current Jobs) | 46 |  | From Current Jobs tab
Total Active Contract Value ($) | 0 |  | Incl. approved COs

## Running TO-DO
July |  | August Mileage
|  | 2025-08-05 | 26 | Miles R/T | Park Towers#211
|  | 2025-08-06 | 22 | Miles R/T | PeaceHealth
|  | 2025-08-08 | 65 | Miles R/T | Mill Plains Zoom | Willamette Falls Pediatric Unit
|  | Total Mileage | 113
|  | 2025 Rate | 0.7 | /Mile
79.1
Potential New Jobs
JDL | New Seasons Treatment
pacific Crest | Pacific Center 5TH Floor
Norwest | Greenburg Pediatric Dentistry